# RED QUEEN v2

Research Protocol & Experiment Ledger

Syntropy LLC · July 2026 · CONFIDENTIAL

# 1. RESEARCH MISSION

Red Queen v2 tests a frontier hypothesis: can multiple AI models achieve "intermodel consensus" by sharing latent vector states rather than exchanging text tokens?

Core Hypothesis (H1):

Models encoding the same semantic input into a shared embedding space will produce latent vectors with cosine similarity > 0.7, enabling geometric consensus without natural language negotiation.

Null Hypothesis (H0):

Different model families encode semantics into incompatible latent spaces. Cross-model vector similarity is indistinguishable from random noise.

# 2. EXPERIMENTAL PROTOCOL

## 2.1 Phase 1 — Homogeneous Control (Week 1-2)

Objective: Validate that the transport and consensus layers work correctly.

Method: Deploy 3 identical model instances (same model family, same weights).

Input: Standardized prompts covering factual, ethical, and creative domains.

Expected: Agreement scores > 0.95. Cosine similarities near 1.0.

Success Criteria: 100 consecutive rounds with agreement > 0.90.

## 2.2 Phase 2 — Heterogeneous Challenge (Week 3-4)

Objective: Test H1 with different model families.

Method: Deploy Kimi, Gemini, and Claude nodes. Each encodes the same prompt using its own internal embedding layer.

Input: Identical prompt set from Phase 1.

Expected: If H1 holds, agreement scores > 0.70. If H0 holds, scores < 0.30.

Success Criteria: Mean agreement score across 100 rounds significantly different from random baseline (p < 0.05).

## 2.3 Phase 3 — Shared Encoder (Week 5-6)

Objective: Test the "common tongue" pragmatic option.

Method: All nodes use the same external embedding API (e.g., OpenAI text-embedding-3-small) to encode prompts before broadcasting.

Input: Same prompt set.

Expected: Agreement scores > 0.90 regardless of model family.

Success Criteria: Demonstrate that shared embedding space enables reliable consensus.

## 2.4 Phase 4 — Adversarial Stress (Week 7-8)

Objective: Test consensus robustness under adversarial conditions.

Method: One node is instructed to deliberately produce "wrong" or contradictory vectors.

Input: Factual prompts where the adversarial node has been misaligned.

Expected: Outlier detection correctly excludes the adversarial node. Consensus among honest nodes remains stable.

Success Criteria: Adversarial node excluded in > 95% of rounds. Honest node agreement > 0.85.

# 3. LOGGING REQUIREMENTS

Every experiment MUST log:

experiment_id (format: RQ-YYYY-MM-DD-NNN)

hypothesis being tested

model versions and embedding dimensions

prompt dataset identifier

round-by-round agreement scores

excluded nodes and exclusion reasons

raw vectors (stored encrypted if containing sensitive data)

Log format: JSONL, one event per line, UTC timestamps.

# 4. ETHICAL GUIDELINES

Never log user-identifiable data in vectors

Encrypt raw vectors at rest if they may encode sensitive prompts

Publish negative results with the same rigor as positive results

Distinguish between "transport works" (engineering) and "telepathy works" (science)

# 5. TEMPLATE: EXPERIMENT LOG ENTRY

{
  "experiment_id": "RQ-2026-07-15-001",
  "phase": "2",
  "hypothesis": "H1",
  "nodes": ["kimi-v1.5", "gemini-1.5-pro", "claude-sonnet-4"],
  "encoder": "internal",
  "prompt_count": 100,
  "rounds_completed": 100,
  "mean_agreement": 0.34,
  "median_agreement": 0.31,
  "std_agreement": 0.12,
  "outlier_rate": 0.67,
  "conclusion": "H0 supported. Cross-model internal embeddings show no convergence.",
  "recommendation": "Proceed to Phase 3 with shared external encoder."
}